## Project Tracker
Task ID | Workstream | Task | Owner | Due Date | Status | Progress % | Dependency | Risk Level | Notes
T-001 | Data | Data Mapping | Alice Chen | 2026-09-10 | Completed | 100 | Source list confirmed | Low | Completed before baseline freeze
T-002 | Data | Data Validation | Brian Li | 2026-09-15 | In Progress | 65 | Vendor extract v3 | High | Blocked by missing field definitions
T-003 | Build | API Integration | Carlos Reed | 2026-09-18 | In Progress | 80 | Interface spec | Medium | On track if QA environment remains available
T-004 | Testing | System Testing | Dina Patel | 2026-09-16 | Not Started | 0 | Data Validation | High | Cannot start until validation defects are closed
T-005 | Change | Training Material Draft | Emily Wong | 2026-09-20 | In Progress | 50 | Process sign-off | Medium | Owner flagged limited SME availability
T-006 | Governance | Steering Committee Pack | Frank Moore | 2026-09-19 | Not Started | 0 | Risk inputs | Medium | Needs decision list by EOD
T-007 | Deployment | Cutover Checklist | Grace Kim | 2026-09-22 | Not Started | 0 | Testing completion | Medium | No confirmed cutover owner yet
T-008 | Data | Defect Retest | Brian Li | 2026-09-17 | In Progress | 40 | Validation fixes | High | Retest queue growing